## 12-Month Conference Planning Checklist

Use this checklist to ensure nothing falls through the cracks. Print it, share it with your team, and check off tasks as you complete each phase.

### Phase 1: Foundation (12-9 Months Out)

- Confirm event dates (check for conflicts with holidays and competing events)

- Research and visit potential venues

- Negotiate and sign venue contract

- Secure hotel room blocks

- Develop preliminary budget

- Define conference theme and content tracks

- Launch call for proposals (if applicable)

### Phase 2: Build-Out (9-6 Months Out)

- Invite and confirm keynote speakers

- Review and select session proposals

- Collect speaker bios, headshots, and session descriptions

- Create sponsorship prospectus and begin outreach

- Finalize exhibit hall layout and booth assignments

- Set up registration system with pricing tiers

- Launch registration with early bird pricing

### Phase 3: Promotion (6-3 Months Out)

- Launch email marketing campaign

- Publish event website with full agenda and speaker details

- Promote on social media channels

- Send early bird deadline reminders

- Finalize session schedule and room assignments

- Submit CEU/CME applications (if applicable)

- Begin program guide design

### Phase 4: Final Preparation (3-1 Months Out)

- Confirm all AV and catering orders

- Order signage, banners, and printed materials

- Prepare attendee badges and name tents

- Send pre-event emails with logistics and schedules

- Assign staff roles and create shift schedules

- Brief volunteers and conduct training

- Finalize catering counts (2 weeks out)

- Confirm transportation and shuttle arrangements

### Phase 5: Event Week

- Walk through all rooms and verify AV setups

- Set up registration and check-in stations

- Place directional signage and sponsor materials

- Hold final staff briefing

- Manage on-site check-ins and walk-up registrations

- Monitor sessions and troubleshoot issues

- Post real-time updates on social media

- Collect lost and found items

### Phase 6: Post-Event (1-4 Weeks After)

- Send thank-you emails to attendees, speakers, and sponsors

- Distribute post-event survey

- Share event photos and session recordings

- Issue CEU/CME certificates

- Compile and analyze survey feedback

- Finalize event financials

- Deliver sponsor reports and metrics

- Conduct staff debrief and document lessons learned

- Secure next year's venue and dates